INDOVISION SERVICES

TA-ATS Platform

Implementation Status & Delivery Roadmap

Talent Acquisition — Applicant Tracking System

Version 1.0  ·  August 2026  ·  Confidential — Internal Use Only

# Table of Contents

# 1. Executive Summary

The TA-ATS platform is live in production (web, desktop + mobile-responsive) with the core recruitment lifecycle operational: authentication & RBAC, dashboards, job-description management with an approval workflow, candidate sourcing & résumé ingestion, a public careers portal with one-click apply, CV ranking, and multi-channel candidate outreach (Email, WhatsApp, SMS).

Against the 128 tracked requirements, roughly 58 are Completed, 37 In Progress, and 33 Pending. The largest remaining areas are the AI Calling / Interview / Evaluation engines and the external Integration layer (Naukri, telephony, calendar), which form the bulk of the "Next" and "Later" roadmap phases.

# 2. Overall Status Snapshot

| Completed | In Progress | Pending |
| --- | --- | --- |
| 58 (45%) | 37 (29%) | 33 (26%) |

Total tracked requirements: 128.

# 3. Module-by-Module Status

| Module | Done | WIP | Pend | Notes / What remains |
| --- | --- | --- | --- | --- |
| Auth, RBAC & Device Binding | 9 | 1 | 4 | Login, JWT, RBAC groups/permissions, admin lock/unlock, login history — done. Pending: device-binding, MFA/SSO, OTP hardening. |
| Dashboard & Configuration | 5 | 1 | 2 | Role dashboards, KPIs, command-center, live activity (polling fallback) — done. Pending: fully drag-config widgets. |
| Job Description Management | 9 | 2 | 1 | JD authoring, approval workflow, viewer tabs, DataTable, public careers, UUID/short-code URLs, LinkedIn share + OG banner — done. |
| Candidate Sourcing & CV Ingestion | 7 | 0 | 4 | Manual upload, résumé parse, careers self-apply, OpenCATS attachments — done. Pending: Naukri/LinkedIn auto-sourcing adapters. |
| CV Ranking Engine | 5 | 3 | 0 | Configurable ranking parameters + scoring service in place. In progress: weight tuning UI, résumé full-text match refinements. |
| Candidate Outreach (Round 1) | 5 | 1 | 1 | Email + WhatsApp (approved template, multi-variable) + SMS, Notify modal, status-change auto-email — delivered this phase. |
| Technical / Second Round | 3 | 3 | 0 | Pipeline stages + interview result capture. In progress: interviewer scheduling + calendar invite polish. |
| Customer / Final Round | 3 | 2 | 1 | Final-round tracking present. Pending: customer-facing scheduling + external calendar sync. |
| AI Calling Engine | 0 | 8 | 3 | Per-candidate AI call controls + screening wired; call status/summary UI. Pending: retry/IVR, telephony provider integration. |
| AI Interview Flow | 0 | 4 | 4 | Screening questions + flow scaffolding. Pending: STT capture, branching, live transcript. |
| AI Evaluation Engine | 1 | 3 | 3 | Ranking hooks exist. Pending: dealbreaker detection, scored evaluation from transcript. |
| Reporting & Notifications | 5 | 1 | 2 | Reports pages, candidate reports, overall dashboard, notification templates — done. Pending: scheduled/emailed reports, richer exports. |
| Configuration Management | 2 | 2 | 1 | Master data (skills, designation, city/state/country, notice, CTC), pipeline stages, rank params, notification templates — largely done. |
| Integration Layer | 0 | 5 | 4 | LinkedIn posting live. In progress: WhatsApp gateway (send2). Pending: Naukri, telephony, Google/Outlook calendar. |
| Mobile API Suite | 4 | 1 | 3 | REST API powers web + is Phase-2 mobile-ready. Pending: FCM/APNs push, offline sync, hybrid app. |

# 4. What We Recently Delivered

Highlights shipped in the current phase:

- Candidate outreach — Email, WhatsApp (send2.digital approved template with multi-variable support), and SMS from a unified Notify modal, plus auto-generated status-change emails on pipeline moves.

- DPDP-style PII masking — phone/email masked in list/table views with reveal-on-click + audit; full values only in detail/edit.

- Server-side pagination — Candidates, Jobs, Clients, Users (fast, scales to thousands of rows) with server-side search & filters.

- Public careers portal — responsive landing + job list/detail, one-click apply, non-enumerable UUID / short encrypted job URLs, LinkedIn share with an auto-generated gradient Open-Graph banner.

- OpenCATS-style candidate attachments (multiple files, primary résumé, private storage, signed download).

- JD approval workflow (submit → hiring-manager approve/reject with emailed deep links) and JD viewer with tabbed details + export.

- UI/UX pass — unified 4-dot loader, responsive navbar with left drawer, mobile-optimised search and candidate profile header.

- Dummy data seeders (1000 JDs, 5000 candidates) and idempotent notification-template seeder.

# 5. Remaining / To Add

- AI Calling Engine — telephony provider integration, automated retry/IVR, call recording pipeline.

- AI Interview Flow — STT capture, question branching, live transcript, dealbreaker detection.

- AI Evaluation Engine — transcript-based scoring, structured evaluation report per candidate.

- Integrations — Naukri sourcing adapter, telephony gateway, Google/Outlook calendar sync for Round 2/3 scheduling.

- Auth hardening — device binding for restricted users, MFA/SSO.

- Reporting — scheduled/emailed reports and richer exports.

- Phase 2 mobile — hybrid app (iOS/Android) on the existing REST API, FCM/APNs push, offline-first sync.

# 6. Delivery Roadmap

## Now (0–1 month) — finish Phase 1 core

- Stabilise production deploy; commit outstanding UI/pagination/outreach work.

- Complete Round 2/3 interviewer scheduling + calendar invite.

- Finalise CV ranking weight-tuning UI.

## Next (1–3 months) — AI + integrations

- Telephony provider + AI Calling Engine (retry/IVR, recording).

- AI Interview Flow (STT, branching, live transcript).

- Naukri sourcing adapter; Google/Outlook calendar sync.

## Later (3–6 months) — evaluation, reporting, hardening

- AI Evaluation Engine (transcript scoring + dealbreakers).

- Scheduled/emailed reports, advanced analytics.

- Device binding, MFA/SSO.

## Phase 2 — Mobile

- Hybrid mobile app on the existing API suite, push notifications, offline sync.

# 7. Notes & Risks

- WhatsApp delivery depends on send2.digital account credentials + server IP whitelisting (external).

- Live-activity WebSocket needs a WS-capable host; on shared hosting it falls back to HTTP polling.

- Module status percentages are indicative, derived from the tracked requirement list and current codebase.