## Siddhi
ATS Testing Large screen
Date | Module | Sub Module | Remarks ( issue ) | Screenshot ( image ) | Status
2026-08-04 | LOGIN(Admin) | Entered wrong email id | No issues |  | Pass
|  | Entered wrong password | No issues |  | Pass
|  | Entered email and password wrong | No issues(resolved) | login-1 | Pass
|  | Kept both the field empty | No issues |  | Pass
| Register(as a candidate) | Entered already existing email id | No issues |  | Pass
|  | Kept phone number empty | No issues | register-1 | Pass
|  | Registeration | No issues |  | Pass
|  | Form pop up | Preferred cities can be anything but it's showing only cities related to the state selected(resolved) | register-2 | Pass
|  |  | Language should be multi select(resolved) | register-3 | Pass
|  |  | experience can't be negative(resolved) | register-4 | Pass
|  | Edit Profile | uploaded resume isn't showing
|  |  | cancel and upload another resume button not working(resolved) | register-5 | Pass
|  |  | not able to change preferred location(resolved) | register-6 | Pass
|  |  | passing year can't be negative (resolved) | register-7 | Pass
|  |  | Percentage can't be negative (resolved) | register-8 | Pass
|  | Apply Jobs | No issues |  | Pass
|  | My applications | when we click on already applied jobs it should display the details of that job(resolved) | register-9 | Pass
|  | Candidate Dashboard | reports, masterdata and groups are still showing | register-10 | Fail
|  | Forget Password | No issues |  | Pass
2026-08-05 | Project Manager | Valid Login | No issues - working fine |  | Pass
|  | Dashboard Cards | Quick actions-assign recruiter is redirecting to random jd's assign recruiter tab(resolved) | dashboard-1 | Pass
|  |  | Total requirements card is working fine |  | Pass
|  |  | Assigned recruiters card is working fine |  | Pass
|  |  | Total submitted is working fine |  | Pass
|  |  | Total shortlisted -I should be able to see that how many candidates I have shortlisted (resolved) |  | Pass
|  |  | Total offered - I should be able to see that how many candidates I have offered (resolved) |  | Pass
|  |  | Total Joined - I should be able to see that how many candidates I have joined (resolved) |  | Pass
|  |  | Total offer rejected - I should be able to see that how many candidates I have rejected the offer (resolved) |  | Pass
|  |  | Total rejected - I should be able to see that how many candidates I have rejected (resolved) |  | Pass
|  |  | Recruitment Funnel card - remove "100% conv"(resolved) | dashboard-2 | Pass
|  |  | Add requirements, view pipeline and reports card working fine |  | Pass
|  |  | Clients filter working fine |  | Pass
|  |  | Clients with same name (G, g) are getting created(resolved) |  | Pass
|  | Job Descriptions | JD is getting posted without filling mandatory fields(resolved) | dashboard-3 | Pass
|  |  | Filters are working fine except the key skills | dashboard-4 | Fail
|  |  | Post history is working fine |  | Pass
|  |  | JD is getting edited under card view even if it's published (resolved) | dashboard-5 | Pass
|  |  | Copy jd, view jd , post jd are working fine |  | Pass
|  |  | View candidate pipeline - notification working | dashboard-6 | Pass
|  |  | Duplicate name JD are getting created (resolved) |  | Pass
|  | Clients | Add client is working fine |  | Pass
|  |  | Whole client module is working fine |  | Pass
|  | Candidates | when click on preview resume - jd template is getting downloaded |  | Fail
|  |  | 5048 candidates are getting loaded together which makes the performance slow |  | Fail
|  | Master Data | Annual CTC is showing even if it doesn't have permission | master-1 | Fail
|  |  | Groups are showing even if it doesn't have permission | master-2 | Fail
| Hiring Manager | Valid Login | working fine |  | Pass
|  | Dashboard | pending approval, approved jds, rejected jds cards are working fine |  | Pass
|  | Job descriptions | Review and it's mail is working |  | Pass
|  | candidate pipeline | notifications under candidate pipeline are working |  | Fail
|  |  | assign candidates working fine |  | Pass
|  |  | recruiters are not getting assigned | HM-1 | Fail
|  |  | Groups are showing even if they don't have permission(In live) | HM-2 | Fail
Master Data are showing even if they don't have permission(In live)
Reports are still showing even if they don't have permission(In live)
2026-08-06 |  |  | On clicking on master menu it is redirecting to the dashboard |  | Fail
|  |  | Reports aren't working |  | Fail
| Recruiter | Valid Login | working fine |  | Pass
|  |  | Admin is not able to assign recruiters to any JD (in some particular JD's) | recruiter-1 | Fail
|  | Dashboard Cards | Assigned JD, active JD, hold JD, closed JD, |  | Pass
|  |  | Screened candidates and pipeline candidates |  | Pass
|  |  | Recruitement metrics is working fine |  | Pass
|  |  | under rejection analysis card - the reason is not displaying (resolved) | recruiter-2 | Pass
|  |  | hide the rejection analysis card as of now |  | Pass
|  |  | one recruiter can't assign a JD to other recruiters |  | Pass
|  |  | bulk notification - cancel and choose another button isn't working (resolved) |  | Pass

## Chirag
ATS Tesing Large screen
Date | Module | Sub Module | Remarks ( issue ) | Screen short ( image ) | Status